## Sheet1
update_id | reported_date | source_type | field_text | site_location | reported_by | benchmark_expected_act | benchmark_intent
UPD-2026-001 | 2026-04-16 | whatsapp_log | Spool erection and field fit-up successfully finished at Manifold A today. | Duliajan Manifold Area A | Ramesh Borah (Piping Foreman) | OIL-PIP-202-A | high_auto_link
UPD-2026-002 | 2026-04-17 | text | Completed right of way ROW clearing, grubbing & grading for Section B pipeline route. | Section B ROW | Diganta Saikia (Pipeline Engr) | OIL-PLN-102-B | high_auto_link
UPD-2026-003 | 2026-04-18 | excel | 100% NDT radiography testing carried out on all 12 weld joints at KP 16 to 30. | Section B KP 16-30 | Sunil Gogoi (QA/QC Inspector) | OIL-PLN-107-B | high_auto_link
UPD-2026-004 | 2026-04-19 | excel | High tension HT cable pulling and routing completed across Feeder C. | Substation Feeder C | Pranab Phukan (Elec Supervisor) | OIL-ELE-403-C | high_auto_link
UPD-2026-005 | 2026-04-20 | whatsapp_log | Dial gauge cold and hot alignment of compressor motor shaft finalized in Shed A. | Compressor Shed A | Ankur Barua (Mechanical Lead) | OIL-MEC-604-A | high_auto_link
UPD-2026-006 | 2026-04-21 | text | Reinforcement steel bar rebar cutting, bending and fixing done for Foundation B. | Compressor Foundation B | Manoj Chetia (Civil Foreman) | OIL-CIV-304-B | high_auto_link
UPD-2026-007 | 2026-04-22 | excel | Horizontal directional drilling HDD river crossing pulled through at Crossing C. | River Crossing C | Subhashish Roy (HDD Incharge) | OIL-PLN-111-C | high_auto_link
UPD-2026-008 | 2026-04-23 | whatsapp_log | Golden tie-in welding at existing header connection completed at Manifold D. | Manifold D Header | Debojit Hazarika (Welding Sup) | OIL-PIP-203-D | high_auto_link
UPD-2026-009 | 2026-04-24 | excel | Bench calibration of pressure and temperature transmitters completed for Batch A. | Field Lab Batch A | Nayan Moni (Inst Engineer) | OIL-INS-504-A | high_auto_link
UPD-2026-010 | 2026-04-25 | text | Installation of 33kV/415V main stepdown transformer completed in Substation A. | Main Substation A | Bhaskar Sarma (Elec Lead) | OIL-ELE-401-A | high_auto_link
UPD-2026-011 | 2026-04-26 | whatsapp_log | Trench padding, backfilling and soil compaction completed KP 31 to 45 Section C. | Pipeline Section C | Bikash Mech (Pipeline Sup) | OIL-PLN-110-C | high_auto_link
UPD-2026-012 | 2026-04-27 | excel | Dyke bund wall civil construction around crude storage Tank B finished up to 2m height. | Crude Tank Dyke B | Rohit Verma (Civil Engr) | OIL-CIV-307-B | high_auto_link
UPD-2026-013 | 2026-04-28 | whatsapp_log | Emergency shutdown valve ESDV stroke testing and calibration carried out at Station D. | ESDV Station D | Pankaj Kalita (Inst Tech) | OIL-INS-507-D | high_auto_link
UPD-2026-014 | 2026-04-29 | text | Flare knockout drum KOD skidded vessel erection placed on foundation at Area B. | Flare Area B | Tapan Dutta (Rigger Lead) | OIL-MEC-602-B | high_auto_link
UPD-2026-015 | 2026-04-30 | excel | Piping spool prefabrication at field workshop Manifold C 42 joints welded. | Yard Manifold C | Jyoti Lahon (Piping QC) | OIL-PIP-201-C | high_auto_link
UPD-2026-016 | 2026-05-01 | whatsapp_log | Hydrotesting done today on line 3 section B, holding 95 bar pressure. | Section B Line 3 | Hiren Das (Site Incharge) | OIL-PIP-205-B | medium_planner_review
UPD-2026-017 | 2026-05-02 | text | Lowering work completed today for pipeline near river bank area. | River Bank Sector | Mukesh Tiwari (Lowering Sup) | OIL-PLN-109-A | medium_planner_review
UPD-2026-018 | 2026-05-03 | excel | PCC layer poured for main compressor block, curing initiated. | Compressor Block | Amitabh Baruah (Civil Sup) | OIL-CIV-303-A | medium_planner_review
UPD-2026-019 | 2026-05-04 | whatsapp_log | Cable tray fixing and cable laying ongoing along the overhead pipe rack. | Overhead Rack Area | Kamal Baruah (Electrician) | OIL-ELE-402-A | medium_planner_review
UPD-2026-020 | 2026-04-15 | excel | Chemical copper earthing pit digging and backfilling with compound completed. | Grid Substation | Bipul Sharma (Elec Contractor) | OIL-ELE-406-B | medium_planner_review
UPD-2026-021 | 2026-04-16 | text | Golden tie-in joint welded at header junction, visual check passed. | Junction Skid | Gaurav Singh (Welding Inspector) | OIL-PIP-203-A | medium_planner_review
UPD-2026-022 | 2026-04-17 | whatsapp_log | Valve pit wall concrete casted today, 18 cum consumed. | Station Valve Pit | Jiten Deka (Civil Supervisor) | OIL-CIV-308-C | medium_planner_review
UPD-2026-023 | 2026-04-18 | excel | Gas compressor skid positioned on foundation bolts with 50 ton crane. | Compressor Shed D | Sanjib Bora (Heavy Rigging) | OIL-MEC-603-D | medium_planner_review
UPD-2026-024 | 2026-04-19 | whatsapp_log | DCS instrument signal checking in progress with control room engineer. | Control Room Loop | Anil Sonowal (Automation Engr) | OIL-INS-508-B | medium_planner_review
UPD-2026-025 | 2026-04-20 | text | Flange bolt torquing and tensioning inspection completed on main skid. | Main Skid Manifold | Kishore Nath (Mechanical Foreman) | OIL-PIP-206-A | medium_planner_review
UPD-2026-026 | 2026-04-21 | whatsapp_log | Stringing of 14-inch coated pipes done for 85 joints along right of way. | ROW Chainage 12 | Suraj Tamang (Pipe Hauler) | OIL-PLN-103-A | medium_planner_review
UPD-2026-027 | 2026-04-22 | excel | Non-shrink epoxy grouting poured below dispatch pump baseplate. | Pump Shed B | Dipen Borpatra (Pump Station Lead) | OIL-MEC-605-B | medium_planner_review
UPD-2026-028 | 2026-04-23 | whatsapp_log | RTU panel installed and terminal wiring connected in local shelter. | RTU Shelter C | Ashim Bhattacharya (SCADA Eng) | OIL-INS-501-C | medium_planner_review
UPD-2026-029 | 2026-04-24 | text | Pigging run tool launched and retrieved successfully with zero damage to cup. | Pig Receiver Station B | Ranjit Moran (Pipeline Operator) | OIL-PLN-112-B | medium_planner_review
UPD-2026-030 | 2026-04-25 | excel | Formwork and water curing of concrete block completed, 14 days finished. | Block C Foundation | Rajib Borgohain (Civil QC) | OIL-CIV-306-C | medium_planner_review
UPD-2026-031 | 2026-04-26 | whatsapp_log | Continuous heavy torrential rain since 9 AM, site completely waterlogged, civil work suspended. | All Sectors | Site Incharge Office | UNMATCHED | low_unmatched_review
UPD-2026-032 | 2026-04-27 | whatsapp_log | Daily safety toolbox meeting conducted with 45 workers regarding working at height and PPE. | Safety Muster Point | HSE Officer Dibrugarh | UNMATCHED | low_unmatched_review
UPD-2026-033 | 2026-04-28 | text | Site DG generator 250 kVA fuel tank filled with 800 liters diesel, oil filter replaced. | DG Yard | Utility Mechanic | UNMATCHED | low_unmatched_review
UPD-2026-034 | 2026-04-29 | excel | Local village panchayat delegation visited site regarding culvert crossing access road. | Village Approach Gate | Liaison Officer | UNMATCHED | low_unmatched_review
UPD-2026-035 | 2026-04-30 | whatsapp_log | Hydraulic excavator CAT 320 broken down due to blown oil hose, mechanic team dispatched. | KP 22 Workshop | Equipment Store Incharge | UNMATCHED | low_unmatched_review
UPD-2026-036 | 2026-05-01 | text | Catering and drinking water delivery received for night shift crew. | Base Camp Mess | Camp Administrator | UNMATCHED | low_unmatched_review
UPD-2026-037 | 2026-05-02 | excel | Third party ISO audit team completed documentation review in admin building. | Conference Hall | QA Auditor | UNMATCHED | low_unmatched_review
UPD-2026-038 | 2026-05-03 | whatsapp_log | Forest department ranger conducted joint boundary pillar verification. | Reserve Forest Boundary | Survey Team 2 | UNMATCHED | low_unmatched_review
UPD-2026-039 | 2026-05-04 | text | Site perimeter floodlights bulb replacement completed on Mast 4. | Perimeter Mast 4 | Maintenance Electrician | UNMATCHED | low_unmatched_review
UPD-2026-040 | 2026-04-15 | whatsapp_log | Scaffolding dismantled from administrative building stairwell. | Admin Building | General Labor Gang | UNMATCHED | low_unmatched_review